## QA Estimation
WBS Estimation for QA
Provide basic information about the project including: Project Title – The proper name used to identify this project; Project Reference / ID - The unique reference or ID for the project; Project Manager - the person with responsibility for the successful delivery of the project to time cost and quality. Project Sponsor - the person ultimately accountable for the success of the project. Prepared by – The person(s) preparing this document; Date/Control Number – The date the plan is finalized and the change or configuration item control number assigned.
Project Title: | Google Search Engine |  | Project Reference / ID: | AQRST-GG-SRCH
Project Manager: | Mr.X |  | Project Sponsor: | Google Client
Prepared by: | Siddhartha |  | Date / Control Number: | A102-000-S2WE
For more tips on completing this template see WBS Excel template
Element Number | WBS Elements Activity, Task, or Sub-Task Name | Definition of Activity or Task (Description) | Responsible Person or Group | Estimated (E) or Actual (A) Cost (Cross reference to budget) | Project Phase (Cross reference to schedule)
The unique reference ID for the activity or task. | Enter the name or title of the Task, Sub-task, Activity or Deliverable. | Provide a brief description of this Activity, Task or Sub-Task. | Enter the person or group who are responsible | Enter the estimate or actual cost of the activity or task or add a cross reference to the budget. | Provide the name or number of the Project phase that this activity falls into.
ID-1 | Requirements Analysis and Sign off / Provide to Team Lead | All the enhancements or client expected requirement should be provided to the QA team. It includes all the activity that needs to be tested in multiple phases. | Product Owner or Project Manager | TBD | Project Initiation
ID-2 | Test Plan Creation | In this document we will define Scope,Objective,Purpose,Entry Exit Criteria, Defect Mgmt Info, Risk Assumptions and RACI Model. | Team Lead/Manager | 6 Hrs | Project Definition and Planning
ID-3 | Test Case Creation | In this document we will cover all Positive and Negative cases for the particular functionality and we will execute those cases on different different Browsers and platform. | QA Team | 12 Hrs | Project Definition and Planning
ID-4 | Test Execution Start(Including Bug Logging) | All the Test Cases will start execution by team on a browsers and platform like Windows,MAC, Mobiles etc. We will also log the found Issues during the testing phases.(SIT,Automation,Performance,Security) | QA Team | 60 Hrs | Project Launch and Execution
ID-5 | Test Execution End(Retesting of Bugs after fixes) | Here we will make sure that applications behave as expected and that the flow of data is maintained for all kinds of user tasks and processes. | QA Team | 30Hrs | Project Launch and Execution
ID-6 | Test Readiness Review Go / No Go | A Test Readiness Review (TRR) provides the formal approval authority with a review showing that the system is ready to enter the test and that the funding and execution of a test executes the test and gathers the required information. | Product Manager/Owner | 4 Hrs | Project Launch and Execution
ID-7 | UAT Testing | Here client test the Application with the requirement and execute their own scenarios on the application. Sometimes clinet want us to test so this UAT is possible with many ways. Alpha,Beta etc. | Client Side People | TBD(we have TAT of 24 Hrs sometime) | Project Launch and Execution
ID-8 | Production Release -GO Live | Here we will migrate application to the Live environment where end user will use it with the help of dev ops team. | QA Team and Clinet People | TBD(Most of the time we do it ASAP like (1 Hr 2Hr ) and we have to provide the sign off to Prod move that Application is working as expected. | Project Closure abd Maintinance